## Defects
Defect-ID | Reg. Date | Description | Fixed Date | Build
1 | 2024-08-20 | 7-seg display for minutes not resetting after re-endering timer-switch (register start of game) or system reset. | 2024-08-20 | 110
2 | 2024-08-24 | Stop watch not stopping when all targets have been hit | 2024-08-24 | 115

## Issues
Issue | Reg. Date | Description | Action | Fixed Date
1 | 2024-08-24 | Target cover to servo attachment is still weak. May fall of after som use.
2 | 2024-08-24 | Not possible to easilly switch of battery power. A manual toggle switch should be included in the battery power circuit.
3 | 2024-08-24 | Range stand does not provide sufficient stable "Game Start" indication. A slight foot-weight change will be detected and cause a restart of the digital stop watch.
4 | 2024-08-24 | Stop watch accuracy not tested. | Use HAL_GetTick() to compare with the generated time …
5 | 2024-08-24 | Sensitivity of the target hit detector are observed to be different.